## Sheet1
WEEK | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22
STARTING DATE | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-15 | 2020-06-22
FYP DEADLINE | 2020-01-27: (Interim Report); 2020-06-01: Abstract and Draft; 2020-06-15: Final Report; 2020-06-22: Presentation
EXTERNAL DEADLINE | 2020-02-10: DL CW; 2020-02-24: ML Img CW; 2020-03-16: - ML Img Exam - DL CW; 2020-03-23: ML Fin CW; 2020-04-27: CF Exam; 2020-05-11: TLDDP Exam
MILESTONES
1 - MVP | bar: 2020-01-27 to 2020-02-24
2 - Mobility | bar: 2020-03-02 to 2020-03-09
3 - Learning Tasks | bar: 2020-03-16 to 2020-03-30
4 - Learning Methods | bar: 2020-04-06 to 2020-04-20
5 - Experiments | bar: 2020-04-27 to 2020-05-18
DOCUMENTATION
Abstract | bar: 2020-05-11 to 2020-05-18
Report Draft | bar: 2020-05-18 to 2020-06-01
Final Report | bar: 2020-06-08 to 2020-06-15
Presentation
CONFIGURATION
Basic config file generator (1) | bar: 2020-01-27
Basic config file loader (1) | bar: 2020-02-03
Configure client mobility (2) | bar: 2020-03-02
Selection of learning task (3) | bar: 2020-03-23
Selection of learning algorithm (4) | bar: 2020-04-06
TRAINING
Client-level minibatch SGD (1) | bar: 2020-02-03 to 2020-02-10
Hierarchical Federated Averaging (1) | bar: 2020-02-10
Large mibatch SGD (4) | bar: 2020-04-13
Local SGD (4) | bar: 2020-04-20
Post-Local SGD (4) | bar: 2020-04-20
MODELS
CNN - MNIST (1) | bar: 2020-02-17
ResNet - CIFAR10 (3) | bar: 2020-03-23
LSTM - Next-word prediction (3) | bar: 2020-03-23 to 2020-03-30
TESTING
Multilevel model testing on test set (1) | bar: 2020-02-24
LOGGING
Top-down logging infrastructure (1) | bar: 2020-02-24
CLIENT MOBILITY
Add mobility functionality (2) | bar: 2020-03-09
TESTING SUITE
Automated scenario testing (5) | bar: 2020-04-27 to 2020-05-04
Simulation results visualizer (5) | bar: 2020-05-04 to 2020-05-11

## Sheet1 (2)
WEEK | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
STARTING DATE | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30
FYP DEADLINE | 2020-01-27: (Interim Report)
EXTERNAL DEADLINE | 2020-02-10: DL CW; 2020-02-24: ML Img CW; 2020-03-16: - ML Img Exam - DL CW; 2020-03-23: ML Fin CW
MILESTONES
1 - MVP | bar: 2020-01-27 to 2020-02-24
2 - Mobility | bar: 2020-03-02 to 2020-03-09
3 - Learning Tasks | bar: 2020-03-16 to 2020-03-30
4 - Learning Methods
5 - Experiments
DOCUMENTATION
Abstract
Report Draft
Final Report
Presentation
CONFIGURATION
Basic config file generator (1) | bar: 2020-01-27
Basic config file loader (1) | bar: 2020-02-03
Configure client mobility (2) | bar: 2020-03-02
Selection of learning task (3) | bar: 2020-03-23
Selection of learning algorithm (4)
TRAINING
Client-level minibatch SGD (1) | bar: 2020-02-03 to 2020-02-10
Hierarchical Federated Averaging (1) | bar: 2020-02-10
Large mibatch SGD (4)
Local SGD (4)
Post-Local SGD (4)
MODELS
CNN - MNIST (1) | bar: 2020-02-17
ResNet - CIFAR10 (3) | bar: 2020-03-23
LSTM - Next-word prediction (3) | bar: 2020-03-23 to 2020-03-30
TESTING
Multilevel model testing on test set (1) | bar: 2020-02-24
LOGGING
Top-down logging infrastructure (1) | bar: 2020-02-24
CLIENT MOBILITY
Add mobility functionality (2) | bar: 2020-03-09
TESTING SUITE
Automated scenario testing (5)
Simulation results visualizer (5)

## Sheet3
WEEK | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22
STARTING DATE | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-15 | 2020-06-22
FYP DEADLINE | 2020-06-01: Abstract and Draft; 2020-06-15: Final Report; 2020-06-22: Presentation
EXTERNAL DEADLINE | 2020-04-27: CF Exam; 2020-05-11: TLDDP Exam
MILESTONES
1 - MVP
2 - Mobility
3 - Learning Tasks
4 - Learning Methods | bar: 2020-04-06 to 2020-04-20
5 - Experiments | bar: 2020-04-27 to 2020-05-18
DOCUMENTATION
Abstract | bar: 2020-05-11 to 2020-05-18
Report Draft | bar: 2020-05-18 to 2020-06-01
Final Report | bar: 2020-06-08 to 2020-06-15
Presentation
CONFIGURATION
Basic config file generator (1)
Basic config file loader (1)
Configure client mobility (2)
Selection of learning task (3)
Selection of learning algorithm (4) | bar: 2020-04-06
TRAINING
Client-level minibatch SGD (1)
Hierarchical Federated Averaging (1)
Large mibatch SGD (4) | bar: 2020-04-13
Local SGD (4) | bar: 2020-04-20
Post-Local SGD (4) | bar: 2020-04-20
MODELS
CNN - MNIST (1)
ResNet - CIFAR10 (3)
LSTM - Next-word prediction (3)
TESTING
Multilevel model testing on test set (1)
LOGGING
Top-down logging infrastructure (1)
CLIENT MOBILITY
Add mobility functionality (2)
TESTING SUITE
Automated scenario testing (5) | bar: 2020-04-27 to 2020-05-04
Simulation results visualizer (5) | bar: 2020-05-04 to 2020-05-11